## Slide 1: Project 8: Internet of Hospital Things (IoHT): Communication to Facilitate Healing REU Student: Kiran Pandit Graduate mentors: Myungho Lee, Kangsoo Kim, Ryan Schubert Faculty Mentor(s): Dr. Greg Welch and Dr. Yier Jin
  Week 4 (June 13 – June 17, 2016)
  Accomplishments:
  Converted libraries for accelerometer from use with Arduino to Photon
  Set up cloud data logger through Particle’s Web IDE
    Can also poll the sensors through command line
  Meeting with Ashley Simmons, Director of Innovation Development at Florida Hospital
    New idea: using phones as existing infrastructure
  Started work on light sensor

## Slide 2: Project 8: Internet of Hospital Things (IoHT): Communication to Facilitate Healing REU Student: Kiran Pandit Graduate mentors: Myungho Lee, Kangsoo Kim, Ryan Schubert Faculty Mentor(s): Dr. Greg Welch and Dr. Yier Jin
  Week 4 (June 13 – June 17, 2016)
Issues/problems encountered and solutions (if any):
  Spent too much time trying to test devices over serial
    Resolved: switched to cloud data logger because that would be useful in long run
  Accelorometer always giving value of 0
    Resolved: was wired for SPI and trying to use I2C
  Light sensor is always giving same (seemingly arbitrary) value
    Need to make sure the I2C protocols are still being properly followed
  Plans for next week:
  Finish setting up sensors: light sensor, motion sensor
  Start processing sound files for unique identifying sounds