## Slide 1
  Week 1 (May 14- May 21 2018)
  Accomplishments:
  Completed CITI Training online (required because my research involves human participants)
  Met with Faculty and Graduate mentors to learn about the project/ research
  Started learning about the Swift language used in iOS app development
  Created tentative schedule for the next 9 weeks
  Set up weekly work sessions for group work and meetings for project updates
  Began researching security risks/concerns associated with IoT device usage
  Problems & Solutions:
  No NID account so I cannot obtain an iRIS account- needed for my project
  Haven’t worked with Swift computer language before- will continue to research and learn about the language
  Plans for next week:
  Continue to work on developing and fixing the app for Android and iOS
  Continue research on security risks/ concerns with IoT devices
  Get access for iRIS account
  Research the differences between the technical implementations between the two platforms
NSF REU Research Experience on Internet of Things 2018
Project #9: Investigating User Benefits and Risks Associated with IoT use REU Student: Kaley Brindisi Graduate mentor: Karla Badillo-Urquiola Faculty Mentor(s): Dr. Wisniewski