## Slide 1
Project #2: IoT and augmented reality: agents with pervasive awareness, appearance, and abilities REU Students: Kendra Richards & Nikhil Mahalanobis
Graduate mentors: Dr. Kangsoo Kim
Faculty mentor(s): Dr. Gregory Welch, Dr. Gerd Bruder
  Week #3 (June 10 – June 13, 2019)
  Accomplishments:
  Got the OptiTrack Trio Camera set up, and got the tracking running on Motive
  Ordered new heart sensor (Polar OH 1), issues with the Empatica E4
  Finally gained IRB approval, ready for testing
  Set the schedule for testing, and hopefully publishing
  Problem & Solutions
  Independent variable of lighting may not be feasible. The Hololense uses visible light to track the world environment
    Use limited lighting
    Might have to dump the variable all-together and change the experiment
  Dividing work
    Each of us choose a variable to work with
    Just write one paper about the experiment, possibly we each write our own paper
  Plans for next week:
  Begin running trials.
  Continue to work on the research paper(s)
  Practice and refine parts of experiment