## Slide 1
Project 2: IoT and augmented reality: agents with pervasive awareness, appearance, and abilities
REU Students: Courtney Harris, Nikolas Yonkers & Connor Flick Faculty mentor(s): Gregory Welch & Gerd Bruder
  Week 6(Monday, June 21 – Friday, June 24 2021)
  Accomplishments:
  Finished AR Gaze method
  Finished development
  Started our study
NSF REU Research Experience on Internet of Things 2021

## Slide 5
Project 2: IoT and augmented reality: agents with pervasive awareness, appearance, and abilities
REU Students: Courtney Harris, Nikolas Yonkers & Connor Flick Faculty mentor(s): Gregory Welch & Gerd Bruder
  Week 6 (Monday, June 21 – Friday, June 24 2021)
  Problem & Solutions
  Debugging and finalizing code
    Solution: took a while but debugged everything
  Voice control tasks during the study were not functioning
    Solution: Changed the tasks to something that could work, throw out data that used old tasks
  Lights were inconsistently changing color, frequently ignoring inputs
    Solution: Avoid sending multiple commands at once, instead focusing on the most relevant ones, in order, at any given time
NSF REU Research Experience on Internet of Things 2021

## Slide 6
Project 2: IoT and augmented reality: agents with pervasive awareness, appearance, and abilities
REU Students: Courtney Harris, Nikolas Yonkers & Connor Flick Faculty mentor(s): Gregory Welch & Gerd Bruder
  Week 6 (Monday, June 21 – Friday, June 24 2021)
  Plans for next week:
  Continue study
  Analyze data
  Write paper
NSF REU Research Experience on Internet of Things 2021