## Slide 1
Project 1: IoT-enabled smart mobility devices for aging and rehabilitation REU Students: Laura Figueroa, Myat Win Faculty mentor(s): Dr. Turgut & Dr. Bӧlӧni
  Week 5 (June 14 – June 18, 2021)
  Accomplishments:
  Additional data collected (dataset 3)
  Linear Regression, Polynomial Regression, Random Forest Regression, and K-Nearest Neighbor Regression Model
  Exported test files into one csv file
  Problem & Solutions
  We had a problem choosing a model to focus on, so we tested all relevant ones to compare their error side by side
  Plans for next week:
  Choose the best model by comparing RSME, R2, and MAE for different datasets
NSF REU Research Experience on Internet of Things 2021

## Slide 2
NSF REU Research Experience on Internet of Things 2021

## Slide 3
NSF REU Research Experience on Internet of Things 2021

## Slide 4
NSF REU Research Experience on Internet of Things 2021

## Slide 5
NSF REU Research Experience on Internet of Things 2021

## Slide 6
NSF REU Research Experience on Internet of Things 2021

## Slide 7
NSF REU Research Experience on Internet of Things 2021

## Slide 8
NSF REU Research Experience on Internet of Things 2021
https://drive.google.com/file/d/1aqFGwBP8j5YIyAtN_UUTAAGXgdPHUOfk/view?usp=sharing