## Slide 1
Project 2: IoT and augmented reality: agents with pervasive awareness, appearance, and abilities
REU Students: Courtney Harris, Nikolas Yonkers & Connor Flick Faculty mentor(s): Gregory Welch & Gerd Bruder
  Week 7 (Monday, June 28 – Friday, July 2 2021)
  Accomplishments:
  Finished User Study
  Drafted research poster
  Began data analysis
  Continued writing research paper
NSF REU Research Experience on Internet of Things 2021

## Slide 2
POSTER GRAPHICS

## Slide 3
USER STUDY

## Slide 4
UEQ DATA
Notes: Pragmatic: dealing with things sensibly and realistically in a way that is based on practical rather than theoretical considerations.
Hedonic: relating to or considered in terms of pleasant (or unpleasant) sensations.

## Slide 5
Project 2: IoT and augmented reality: agents with pervasive awareness, appearance, and abilities
REU Students: Courtney Harris, Nikolas Yonkers & Connor Flick Faculty mentor(s): Gregory Welch & Gerd Bruder
  Week 7 (Monday, June 28 – Friday, July 2 2021)
  Problem & Solutions
  Lights had connectivity issues during study
    Solution: WiFi interference issues causing it, reset the app and Hue Bridge to change local Zigbee channels
  The Alexa app cannot play media outside of music (with VERY limited exception)
    Solution: Updated the task slides to reflect limitations
  Participants cancelled or showed up late causing us to have less data.
    Solution: We still have enough data to have a thorough analysis
NSF REU Research Experience on Internet of Things 2021

## Slide 6
Project 2: IoT and augmented reality: agents with pervasive awareness, appearance, and abilities
REU Students: Courtney Harris, Nikolas Yonkers & Connor Flick Faculty mentor(s): Gregory Welch & Gerd Bruder
  Week 7(Monday, June 28 – Friday, July 2 2021)
  Plans for next week:
  Finalize and print poster
  Continue writing research paper
  Present work at symposium
NSF REU Research Experience on Internet of Things 2021