## Slide 1
NSF REU Research Experience on Internet of Things 2022
Project #:4 Machine learning-based disaster resilient microgrid design and management
REU Students: Paco-Jaleel Balthazar, Anthony Bishop-Gylys
Graduate Students: Fazlullah Hakimi Faculty mentor(s): Qun Zhou Sun, Damla Turgut.
  Week #4 (June 6- June 10)
  Accomplishments:
  Documented the structure of the Pymgrid simulator
  Finished compiling data on remaining energy storage devices
  Implemented second timescale processing to parts of the Pymgrid simulator
  Problem & Solutions
  Problem: All data was not on a 1 second timescale
  Solution: Automatic interpolation function implemented to convert all Pymgrid data to 1 second timescale using linear interpolation
  Plans for next week:
  Finish implementing second timescale data processing to Pymgrid
  Start the mid-term report
  Finalize literature report and source sorting
  Compile more data to feed simulator

## Slide 2
NSF REU Research Experience on Internet of Things 2022
Project #:4 Machine learning-based disaster resilient microgrid design and management
REU Students: Paco-Jaleel Balthazar, Anthony Bishop-Gylys
Graduate Students: Fazlullah Hakimi Faculty mentor(s): Qun Zhou Sun, Damla Turgut
  Week #4 (June 6 - June 10)
Themes:
Simulator modifications, data formatting, and custom class creation

## Slide 3: Committing Pymgrid’s structure to memory
We developed a 71-slide presentation on how each function in the Pymgrid simulator is implemented, including its outputs and inputs.
Pymgrid has a total of 67 individual function (__init__ functions included)
NSF REU Research Experience on Internet of Things 2022

## Slide 4: Data interpolated
Data interpolation involves estimating a value based on its surrounding values.
Most data we found was in the wrong timescale, an interpolation loop was needed
NSF REU Research Experience on Internet of Things 2022

## Slide 5
NSF REU Research Experience on Internet of Things 2022
Load data before interpolation
Load data after interpolation

## Slide 6: Interpolation Function
NSF REU Research Experience on Internet of Things 2022
def inter(df,original_size):
i=1
while True:
if df.shape[0] == DAY:
df = df.interpolate()
return df
elif i % 2 != 0:
if i > (original_size*2)-1:
df = df.interpolate(method='linear')
return df
else:
np_arr = df.to_numpy(dtype=float)
np_arr = np.insert(np_arr,i, np.nan)
df = pd.DataFrame(np_arr, columns=['Value'],)
i = i+1
For aspiring data scientists: Converting a dataframe into a numpy array and working on it directly sometimes works faster than doing operations on it directly.

## Slide 7: Energy Storage Modeling
Refined input data for easier human and machine readability
Documented Storage class in code
Debugged and prepared Storage class for integration
NSF REU Research Experience on Internet of Things 2022

## Slide 8: Previous self-discharge function
y = 0.1
NSF REU Research Experience on Internet of Things 2022

## Slide 9: Complicated self-discharge function
y =
-(233189*e^(-(493*((-(10^12*ln(-e^-((100x-2855)/473)+1)+275221.68)/0.3944)-3275300))/(1.25*10^15)-1567/10^9))/((1.25*10^17)*(1-e^(-(493*((-(10^12*ln(-e^-((100x-2855)/473)+1)+275221.68)/0.3944)-3275300))/(1.25*10^15)-1567/10^9)))
NSF REU Research Experience on Internet of Things 2022

## Slide 10: Simplified self-discharge function
[3] T. Deutschen, S. Gasser, M. Schaller, and J. Siehr, “Modeling the self-discharge by voltage decay of a NMC/graphite lithium-ion cell,” J. Ener. Stor., vol. 19. Elsevier BV, pp. 113–119, Oct. 2018. doi: 10.1016/j.est.2018.07.003.

## Slide 11: Old and New Energy Storage Data Tables
Complicated Energy Storage Model
NSF REU Research Experience on Internet of Things 2022
Refined Energy Storage Model

## Slide 12: Next Steps
How do we take the simulator from only using
to using
in a way that produces a realistic model while remaining simple and straightforward enough for open-source interaction?
Notes: We’re going to document well
We’re going to take a step back every so often and take a look at our code to make sure we’re not doing anything in a roundabout way
We’re going to look at previously written code to see if we still understand it